## Task and Activities
Task | Focal Point | Duration (hrs) | Week | Status | Domain | Comments | Domains | Guidelines
HR orientation | https://wiki.proofpoint.com/wiki/display/HR/Human+Resources+Wiki?src=breadcrumbs-parent | 3 | 1 | done | Other |  | Product
Intro to CASB and Cloud Security | Itai/Yoel | 1 | 1 | done | Product |  | Process
Product Training | https://www.traininglevelup.com/#product_cloud-app-security-broker | 15 | 1 | done | Product |  | Strategy | Week 3: Tech Deep dives, Engineering, processes
Doc review (User guide, best practices+deployment guide) | https://proofpointcommunities.force.com/community/s/article/Proofpoint-CASB-All-Proofpoint-CASB-Guides | 8 | 1 | done | Product
Hands on eval of CASB | Self | 5 | 1 | done | Product |  | Technical | Week 1: Intro to proofpoint, CASB overview, AAC deep dive
Hands on eval of TSD | Itai Zauer | 1 | 1 | s | Product |  | Market | Week 2: CASB Pillas and Tech deep dives
Employee kickof | https://wiki.proofpoint.com/wiki/display/PFPT/Employee+Kick-Off+2022 | 1.5 | 1 | done | Other |  | Other | Week 4: Marketing, Sales, ATG, Platform, Other products
Organizational chart and structure | Itai/Yoel | 0.5 | 1 | done | Process
Cloud security group Vision, strategy and GTM | Yoel | 1 | 1 | done | Strategy
Intro and Cloud DLP overview | Itai Zauer | 1.5 | 1 | done | Product
Intro Roey Kosovski (API Team Leader) | Roey | 0.5 | 1 | done | Technical
CASB/SSE personas | https://proofpoint.invisionapp.com/overview/CASB-Personas-cktz15qof4trd01zmc8vird1d/screens?sortBy=1&sortOrder=1&viewLayout=2 | 0.5 | 1 | done | Product
Introduction + Threat + 3PA domain overview | Dafna Paz | 1.5 | 2 | done | Product
CASB competitive landscape | Self +Seismic | 15 | 2 | done | Market
Pricing and licensing, SKUs | Yoel | 0.5 | 2 | done | Product
CASB Roadmap review (next 2 Qtrs.) | Yoel | 3 | 2 | done | Product
App governance and NCRE | Bernard | 0.5 | 2 | done | Technical
CASB AAC+CSPM overview | Bernard + Presentation | 0.5 | 2 | done | Product
Project X overview | Yoel | 0.5 | 2 | done | Product
Intro with Nancy+ Overview of CASB docs process and guides | Nancy Sweeney | 0.5 | 2 | done | Product
Intro to CPE team and support process | Chen/Kalia/Danna | 1 | 2 | done | Product | can combine with support processes
Review PRDs and Specs | https://firelayers.atlassian.net/wiki/spaces/PRD/overview | 30 | 3 | done | Product
SKO sessions for Information protection and cloud security | 2 recordings: https://proofpoint.seismic.com/Link/Content/DCptIlGUSNfkmqM_Dl23Xipw#/?anchorId=fcb16d1b-589a-421a-8dfa-b4b60a8316c2 https://proofpoint.seismic.com/Link/Content/DCptIlGUSNfkmqM_Dl23Xipw#/?anchorId=1a6f0224-77b1-418b-a6a5-64719b10b327 | 1.5 | 3 | done | Sales
Review select CASB Demos from 2020-2021 | https://firelayers.atlassian.net/wiki/spaces/PRD/pages/77170475050/Demo+Library | 4 | 3 | done | Product
Intro Nadav Hershkovitz (Dir of CASB Engineering) | Nadav Hershkovitz | 0.5 | 3 | done | Technical | Dir - CASB -> Tal T
Intro Shlomi Shor (Engine Team Leader) | Shlomi Shor | 0.5 | 3 | done | Technical | Eng Mgr - CASB Engine and AppGov
Intro Alin | Alin | 0.5 | 3 | s | Product
CASB Architecture overview | alexander | 4 | 3 | done | Technical
Intro Idan Naim (UI Team Leader) | Idan Naim | 0.5 | 3 | done | Technical
Product work procedures | Yoel/Itai | 1 | 3 | done | Process
Work processes working with the platform team | Yogev | 0.5 | 3 | done | Process
Intro and overview of Feature development lifecycle | Ifat | 0.5 | 4 |  | Process
Jira, opening tickets+ Protfolio deep dive | Ifat | 0.5 | 4 |  | Process
Running demos | Yoel/Itai/ATG | 1 | 4 |  | Sales
Product Analytics | Yoel | 2 | 4 |  | Product
CASB deployment deep dive | Danna/Kalia | 1 | 4 |  | Product
Review marketing colleteral and data sheets | Self (seismic), Material from Sai | 2 | 4 |  | Market
Review compeitive material and recent Analyst reports | Self on Seismic / Geoff Vicas | 4 | 4 |  | Market
Roles and responsibilities | Itai | 1 | 4 |  | Other
Goals for 2022 | Itai | 1 | 4 |  | Other
ATG intros | During ATG-PM meeting | 1 | 4 |  | Sales
Field enablement processes (Demo, ATG sync, Tech summit, CSM focal points) | Itai / Yoel | 0.5 | 4 |  | Process